## Summary
HR PAYROLL SYSTEM - TEST EXECUTION SUMMARY
Generated: 2025-11-03 20:21:39
TEST ENVIRONMENT
Frontend URL: | http://127.0.0.1:5174
Backend API: | http://127.0.0.1:8000
API Docs: | http://127.0.0.1:8000/docs
TEST CREDENTIALS
Role | Username | Password | Purpose
SaaS Admin | saasadmin | admin123 | System-wide administration
Employer Admin | employer | employer123 | Company HR management
Employee | employee1 | employee123 | Employee self-service
TEST EXECUTION PROGRESS
Category | Total | Passed | Failed | Blocked | Not Tested | Pass %
SaaS Admin | 11 | 0 | 0 | 0 | 11 | 0%
Employer Admin | 49 | 0 | 0 | 0 | 49 | 0%
Employee | 22 | 0 | 0 | 0 | 22 | 0%
Cross-Functional | 12 | 0 | 0 | 0 | 12 | 0%
Integration | 5 | 0 | 0 | 0 | 5 | 0%
UI/UX | 9 | 0 | 0 | 0 | 9 | 0%
Regression | 10 | 0 | 0 | 0 | 10 | 0%
TOTAL | 118 | 0 | 0 | 0 | 118 | 0%
PRIORITY BREAKDOWN
Priority | Count | Status
Critical | 48 | Not Started
High | 49 | Not Started
Medium | 20 | Not Started
Low | 1 | Not Started

## SaaS_Admin
SaaS Admin - Test Cases
TC ID | Test Case | Test Steps | Expected Result | Priority | Status | Tester | Date | Comments | Bug ID
SA-001 | SaaS Admin Login | Navigate to login, enter saasadmin/admin123, click Sign In | Login successful, redirected to dashboard | Critical | Not Tested
SA-002 | Session Persistence | Login as saasadmin, refresh browser | User remains logged in | High | Not Tested
SA-003 | Logout | Login as saasadmin, click logout | Logged out, redirected to login | High | Not Tested
SA-004 | Invalid Credentials | Enter wrong password, click Sign In | Error message displayed | Medium | Not Tested
SA-010 | Dashboard View | Login as saasadmin, verify dashboard loads | Dashboard displays with statistics | Critical | Not Tested
SA-011 | Navigation Menu Access | Check sidebar menu | All admin menu items visible | High | Not Tested
SA-020 | Access System Config | Navigate to Admin > System Config | System config page loads | High | Not Tested
SA-021 | View Configuration Settings | Check all tabs | All config tabs display correctly | Medium | Not Tested
SA-022 | Update System Settings | Modify a setting, click Save | Settings updated successfully | High | Not Tested
SA-030 | View All Tenants | Navigate to tenants section | List of all tenants displayed | High | Not Tested
SA-031 | Access Cross-Tenant Data | Switch between tenants | Can view data from multiple tenants | Critical | Not Tested

## Employer_Admin
Employer Admin - Test Cases
TC ID | Test Case | Test Steps | Expected Result | Priority | Status | Tester | Date | Comments | Bug ID
EA-001 | Employer Admin Login | Login with employer/employer123 | Login successful, redirected to dashboard | Critical | Not Tested
EA-002 | Session Persistence | Login, refresh browser | User remains logged in | High | Not Tested
EA-003 | Logout | Click logout | Logged out successfully | High | Not Tested
EA-004 | Tenant Data Isolation | View employees list | Only sees own tenant employees | Critical | Not Tested
EA-010 | Dashboard Statistics | View dashboard | Shows total, active, exited, attendance % | Critical | Not Tested
EA-011 | Location Filter | Select location from dropdown | Statistics update for location | Medium | Not Tested
EA-020 | View Employees List | Navigate to Employees | List displayed with filters | Critical | Not Tested
EA-021 | Search Employee | Enter name in search | Matching employees shown | High | Not Tested
EA-022 | Filter Employees | Apply filters (status, location, dept) | Filtered results displayed | High | Not Tested
EA-023 | Add New Employee | Click Add, fill fields, save | Employee created successfully | Critical | Not Tested
EA-024 | View Employee Details | Click on employee | Details page displayed | High | Not Tested
EA-025 | Edit Employee | Click Edit, modify, save | Employee updated | High | Not Tested
EA-026 | Delete Employee | Select employee, delete, confirm | Employee deleted/archived | High | Not Tested
EA-027 | Bulk Upload Employees | Click Upload, select Excel, upload | Employees imported from Excel | High | Not Tested
EA-028 | Export Employees | Click Export, select format | Employee data exported | Medium | Not Tested
EA-030 | View Locations | Navigate to Locations | List of locations displayed | High | Not Tested
EA-031 | Add New Location | Click Add, fill details, save | Location created | High | Not Tested
EA-032 | Edit Location | Click Edit, modify, save | Location updated | Medium | Not Tested
EA-033 | Delete Location | Select location, delete | Location deleted if no employees | Medium | Not Tested
EA-040 | View Attendance | Navigate to Attendance | Attendance records with filters | Critical | Not Tested
EA-041 | Filter by Date Range | Select dates, apply filter | Attendance for period shown | High | Not Tested
EA-042 | Filter by Location | Select location, apply | Attendance for location shown | High | Not Tested
EA-043 | Mark Attendance | Select date, mark present/absent | Attendance marked successfully | Critical | Not Tested
EA-044 | Bulk Upload Attendance | Upload Excel file | Attendance imported | High | Not Tested
EA-045 | Export Attendance | Select range, export | Attendance exported | Medium | Not Tested
EA-050 | View Wage Structure | Navigate to Wages | Wage components displayed | High | Not Tested
EA-051 | Define Wage Components | Add component, save | Component created | High | Not Tested
EA-052 | Assign Wages to Employee | Select employee, assign structure | Wages assigned | Critical | Not Tested
EA-060 | View Leave Requests | Navigate to Leaves | Leave requests displayed | Critical | Not Tested
EA-061 | Filter Leave Requests | Filter by status | Filtered requests shown | High | Not Tested
EA-062 | Approve Leave Request | Click on request, approve | Leave approved | Critical | Not Tested
EA-063 | Reject Leave Request | Click on request, reject | Leave rejected with reason | Critical | Not Tested
EA-064 | View Leave Balance | Select employee, view balance | Leave balance shown by type | High | Not Tested
EA-070 | View Payroll Dashboard | Navigate to Payroll | Payroll dashboard displayed | Critical | Not Tested
EA-071 | Process Monthly Payroll | Select month, process payroll | Payroll processed for all | Critical | Not Tested
EA-072 | View Payroll Details | Select month, click employee | Detailed salary slip shown | Critical | Not Tested
EA-073 | Apply Deductions | Select employee, add deduction | Deduction applied | High | Not Tested
EA-074 | Generate Pay Slips | Select month, generate | Pay slips generated | Critical | Not Tested
EA-075 | Download Pay Slips | Select month, download | Pay slips downloaded | High | Not Tested
EA-080 | View Statutory Reports | Navigate to Statutory | Statutory dashboard shown | High | Not Tested
EA-081 | Generate PF Report | Select PF, choose dates, generate | PF report generated | High | Not Tested
EA-082 | Generate ESI Report | Select ESI, choose dates, generate | ESI report generated | High | Not Tested
EA-090 | View Bank Transfer | Navigate to Bank Transfer | Bank transfer dashboard shown | High | Not Tested
EA-091 | Generate Bank File | Select month, choose format, generate | Bank file generated | Critical | Not Tested
EA-092 | Download Bank File | Generate, download, choose format | Bank file downloaded | High | Not Tested
EA-100 | View Reports Dashboard | Navigate to Reports | Reports dashboard with categories | High | Not Tested
EA-101 | Employee Report | Select Employee Report, generate | Employee report generated | Medium | Not Tested
EA-102 | Attendance Report | Select Attendance Report, generate | Attendance report generated | High | Not Tested
EA-103 | Payroll Summary Report | Select Payroll Summary, generate | Payroll summary generated | High | Not Tested

## Employee
Employee - Test Cases
TC ID | Test Case | Test Steps | Expected Result | Priority | Status | Tester | Date | Comments | Bug ID
EM-001 | Employee Login | Login with employee1/employee123 | Login successful, redirected to dashboard | Critical | Not Tested
EM-002 | Session Persistence | Login, refresh browser | User remains logged in | High | Not Tested
EM-003 | Logout | Click logout | Logged out successfully | High | Not Tested
EM-004 | Restricted Access | Try to access employer pages | Access denied | Critical | Not Tested
EM-010 | View Dashboard | View dashboard | Shows personal stats, attendance, leaves | Critical | Not Tested
EM-011 | Quick Actions | Check quick action buttons | Shows apply leave, view payslip | Medium | Not Tested
EM-020 | View Profile | Navigate to Profile | Complete profile info displayed | High | Not Tested
EM-021 | Update Personal Info | Click Edit, update fields, save | Personal info updated | High | Not Tested
EM-022 | Upload Profile Photo | Click upload, select image, upload | Profile photo updated | Low | Not Tested
EM-023 | View Employment Details | View employment tab | Shows designation, dept, joining date | Medium | Not Tested
EM-024 | View Bank Details | View bank details section | Bank info displayed (masked) | Medium | Not Tested
EM-025 | Change Password | Click Change Password, enter old/new | Password changed | High | Not Tested
EM-030 | View Attendance | Navigate to My Attendance | Personal attendance records shown | Critical | Not Tested
EM-031 | View Attendance Calendar | View calendar | Calendar shows present/absent/leave | Medium | Not Tested
EM-033 | Apply for Leave | Click Apply, select type/dates, submit | Leave application submitted | Critical | Not Tested
EM-034 | View Leave Balance | View balance section | Available leave balance shown | High | Not Tested
EM-035 | View Leave History | View history tab | Past leave requests with status | Medium | Not Tested
EM-036 | Cancel Leave Request | Select pending request, cancel | Leave request cancelled | Medium | Not Tested
EM-040 | View Payslips | Navigate to Payslips | List of payslips by month | Critical | Not Tested
EM-041 | View Payslip Details | Click on a month | Detailed payslip shown | Critical | Not Tested
EM-042 | Download Payslip | Select month, download PDF | Payslip downloaded as PDF | Critical | Not Tested
EM-043 | View Salary Breakdown | View payslip breakdown | Shows earnings, deductions, net pay | High | Not Tested

## Cross-Functional
Cross-Functional - Test Cases
TC ID | Test Case | Test Steps | Expected Result | Priority | Status | Tester | Date | Comments | Bug ID
CF-001 | Concurrent User Access | Login multiple users simultaneously | All users work without conflicts | High | Not Tested
CF-002 | Data Isolation | Add data as employer, login as employee | Employee sees only own data | Critical | Not Tested
CF-003 | Leave Approval Flow | Apply leave as employee, approve as employer | Leave status updated across roles | Critical | Not Tested
CF-010 | Token Expiration | Login, wait for token expiry, perform action | Redirected to login | Critical | Not Tested
CF-011 | SQL Injection Prevention | Try SQL injection in fields | Input sanitized, no execution | Critical | Not Tested
CF-012 | XSS Prevention | Enter script tags in fields | Scripts escaped, not executed | Critical | Not Tested
CF-013 | CSRF Protection | Attempt CSRF attack | Request blocked | Critical | Not Tested
CF-014 | Password Security | Create user, check database | Password stored as hash | Critical | Not Tested
CF-020 | Large Dataset Handling | Upload 1000+ employees, navigate | Page loads with pagination | Medium | Not Tested
CF-030 | API Failure Handling | Stop backend, try action | User-friendly error shown | High | Not Tested
CF-031 | Network Error | Disconnect internet, try action | Appropriate error shown | High | Not Tested
CF-032 | Invalid File Upload | Upload invalid file type | Error message, file rejected | Medium | Not Tested

## Integration
Integration - Test Cases
TC ID | Test Case | Test Steps | Expected Result | Priority | Status | Tester | Date | Comments | Bug ID
INT-001 | API Authentication | Call protected endpoint without token | 401 Unauthorized returned | Critical | Not Tested
INT-002 | API with Valid Token | Login, call endpoint with token | 200 OK, data returned | Critical | Not Tested
INT-003 | API Response Format | Call any endpoint, check response | Consistent JSON format | High | Not Tested
INT-010 | Data Persistence | Add employee, restart server, check | Data persists across restart | Critical | Not Tested
INT-011 | Transaction Rollback | Perform failing transaction, check DB | Partial data not saved | High | Not Tested

## UI_UX
UI/UX - Test Cases
TC ID | Test Case | Test Steps | Expected Result | Priority | Status | Tester | Date | Comments | Bug ID
UI-001 | Responsive Design - Desktop | Open on desktop (1920x1080) | UI displays properly | High | Not Tested
UI-002 | Responsive Design - Tablet | Open on tablet (768x1024) | UI adapts to tablet | Medium | Not Tested
UI-003 | Responsive Design - Mobile | Open on mobile (375x667) | Mobile-optimized layout | Medium | Not Tested
UI-004 | Browser - Chrome | Test all features in Chrome | All features work | Critical | Not Tested
UI-005 | Browser - Firefox | Test all features in Firefox | All features work | Medium | Not Tested
UI-006 | Browser - Edge | Test all features in Edge | All features work | Medium | Not Tested
UI-007 | Loading States | Perform async operation | Loading indicator shown | High | Not Tested
UI-008 | Success Messages | Perform successful operation | Success message displayed | High | Not Tested
UI-009 | Error Messages | Trigger validation error | Clear error message shown | High | Not Tested

## Regression
Regression - Test Cases
TC ID | Test Case | Test Steps | Expected Result | Priority | Status | Tester | Date | Comments | Bug ID
REG-001 | Application Starts | Start frontend and backend | Servers start without errors | Critical | Not Tested
REG-002 | Login Works | Login with all three roles | All logins successful | Critical | Not Tested
REG-003 | Dashboard Loads | View dashboard for each role | Dashboards display correctly | Critical | Not Tested
REG-004 | Navigation Works | Navigate between all pages | Navigation successful | Critical | Not Tested
REG-005 | Logout Works | Logout for all roles | Logout successful | Critical | Not Tested
REG-010 | Employee CRUD | Create, read, update, delete employee | All operations successful | Critical | Not Tested
REG-011 | Attendance Operations | Mark and view attendance | Operations successful | Critical | Not Tested
REG-012 | Leave Operations | Apply and approve leaves | Operations successful | Critical | Not Tested
REG-013 | Payroll Processing | Process monthly payroll | Payroll processed successfully | Critical | Not Tested
REG-014 | Report Generation | Generate and export reports | Reports generated successfully | Critical | Not Tested

## Bug_Tracking
BUG TRACKING LOG
Bug ID | TC ID | Summary | Description | Severity | Priority | Status | Assigned To | Date Found | Date Fixed