## 📊 Overview
HR PAYROLL SYSTEM — PROJECT TRACKER
Symbiosis HR & Payroll ¦ Last Updated: 08 Mar 2026 ¦ Stack: FastAPI + React + PostgreSQL
Total Features |  | Complete |  | In Progress |  | Not Started/Stub |  | Overall Progress |  | Client Approved
60 |  | 32 |  | 14 |  | 14 |  | 61% |  | 24
STAKEHOLDER-WISE FEATURE PROGRESS
Stakeholder | Total Features | Complete | In Progress | Not Started | Completion % | Client Approval | Priority | Notes
| SaaS Admin | 7 | 4 | 2 | 1 | 57% | In Review | High | Tenant & billing mgmt core done
| Employer/HR | 23 | 14 | 6 | 3 | 61% | In Review | High | Payroll & leave done; reports pending
| Employee | 9 | 7 | 1 | 1 | 78% | Approved | High | Self-service portal mostly complete
| Auditor | 5 | 2 | 1 | 2 | 40% | Pending | Medium | Audit trail & reports partially done
| System/Platform | 16 | 5 | 4 | 7 | 31% | Pending | Medium | Auth done; notifications & integrations pending
| TOTAL | 60 | 32 | 14 | 14 | 61% | —
STATUS LEGEND
Complete
In Progress
Partial
Not Started
Stub/Placeholder
API Ready / UI Pending

## 👤 SaaS Admin
SAAS ADMIN — FEATURE TRACKING
HR Payroll System ¦ 08 Mar 2026
Total |  | 7
Complete |  | 2
In Progress |  | 2
Partial |  | 0
Not Started |  | 0
API Only |  | 3
Progress % |  | 64%
# | Module | Feature | Description | Backend Status | Frontend Status | Overall Status | Client Approval | Priority | Notes
1 | Authentication | Login / JWT Auth | Username + password, JWT token generation | Complete | Complete | Complete | Approved | High
2 | Tenant Management | Create / List / Update Tenants | Multi-tenant org creation and management | Complete | In Progress | In Progress | In Review | High | API complete; SaaS admin UI partial
3 | Tenant Management | Tenant Dashboard | Tenant KPIs and overview | Complete | Complete | Complete | In Review | High
4 | Registration | Organisation Registration | New org registration with review workflow | Complete | Not Started | API Ready / UI Pending | Pending | High | Backend + review endpoints done; no UI page yet
5 | Billing | Subscription Plans CRUD | Create, list, update pricing plans | Complete | Not Started | API Ready / UI Pending | Pending | Medium | BillingComponents.jsx stub exists
6 | Billing | Subscription & Invoice Mgmt | Tenant subscription lifecycle + invoice tracking | Complete | Not Started | API Ready / UI Pending | Pending | Medium | Full API done; no UI wired
7 | System Config | System Configuration UI | Initialise config, view system settings | Complete | In Progress | In Progress | Pending | Medium | SystemConfig.jsx exists; partial implementation

## 🏢 Employer-HR
EMPLOYER / HR — FEATURE TRACKING
HR Payroll System ¦ 08 Mar 2026
Total |  | 23
Complete |  | 19
In Progress |  | 2
Partial |  | 1
Not Started |  | 1
API Only |  | 0
Progress % |  | 89%
# | Module | Feature | Description | Backend Status | Frontend Status | Overall Status | Client Approval | Priority | Notes
1 | Dashboard | Employer Dashboard | Employee count, attendance, recent activity KPIs | Complete | Complete | Complete | Approved | High
2 | Employee Mgmt | Employee List & Search | List, search, filter employees | Complete | Complete | Complete | Approved | High
3 | Employee Mgmt | Add / Edit Employee | Create and update employee basic info | Complete | Complete | Complete | Approved | High
4 | Employee Mgmt | Employee Detail (All Tabs) | Bank, salary, statutory, contact, employment tabs | Complete | Complete | Complete | Approved | High | 6-tab detail form fully wired
5 | Employee Mgmt | Bulk Employee Upload | Excel upload for mass employee onboarding | Complete | Complete | Complete | Approved | High | Template download + upload working
6 | Attendance | Attendance Record Entry | Manual single attendance entry | Complete | Complete | Complete | Approved | High
7 | Attendance | Bulk Attendance Upload | Excel template download + upload | Complete | Complete | Complete | Approved | High
8 | Attendance | Attendance Dashboard Stats | Today present/absent/late stats | Partial | Partial | Partial | Pending | Medium | TODO comment in EmployerDashboard.jsx; API not wired
9 | Leave Mgmt | Leave Request List | View all leave requests with filter | Complete | Complete | Complete | Approved | High
10 | Leave Mgmt | Approve / Reject Leave | One-click approval/rejection with remarks | Complete | Complete | Complete | Approved | High
11 | Leave Mgmt | Leave Type Management | Create, update, delete leave types | Complete | In Progress | In Progress | Pending | Medium | API complete; no dedicated UI for leave type CRUD
12 | Payroll | Bulk Payroll Processing | Calculate payroll for all employees in a month | Complete | Complete | Complete | Approved | High
13 | Payroll | Wage Statement List & Approval | View, approve, mark-paid wage statements | Complete | Complete | Complete | Approved | High | PayrollDashboard + Payroll pages
14 | Payroll | Payslip PDF Download | Per-employee payslip PDF generation | Complete | Complete | Complete | Approved | High | Professional layout with Indian currency words
15 | Payroll | Salary Register Download | Full month salary register Excel | Complete | Complete | Complete | Approved | High
16 | Payroll | Bank Transfer File | Bank-ready transfer file (CSV/NEFT) | Complete | Complete | Complete | Approved | High | BankTransfer.jsx wired
17 | Payroll | Bulk Payslip Email | Send payslips via email to all employees | Complete | Complete | Complete | In Review | Medium | SMTP config required in .env
18 | Holiday Calendar | Holiday Add / Edit / Delete | Manage company holidays with calendar view | Complete | Complete | Complete | Approved | High | Color-coded calendar UI
19 | Holiday Calendar | Working Calendar (Weekly Offs) | Configure weekly off days per location | Complete | Complete | Complete | Approved | High
20 | Statutory | EPF-ECR / ESI / PT / PF Downloads | Statutory compliance file generation | Complete | Complete | Complete | In Review | High | 5 forms: EPF-ECR, ESI, PT-FormV, FormXIII, PF-Challan
21 | Org Structure | Dept / Designation / Grade CRUD | Organisation structure management | Complete | In Progress | In Progress | Pending | Medium | API done; no dedicated UI page, used in dropdowns
22 | Locations | Location Management | Add, edit, list company locations | Complete | Complete | Complete | Approved | Medium
23 | Reports | Attendance & Payroll Reports | Downloadable reports for HR | Partial | Stub/Placeholder | Stub/Placeholder | Pending | Medium | Reports.jsx shows 'coming soon'; 2 basic API stubs

## 👨‍💼 Employee
EMPLOYEE — FEATURE TRACKING
HR Payroll System ¦ 08 Mar 2026
Total |  | 9
Complete |  | 8
In Progress |  | 1
Partial |  | 0
Not Started |  | 0
API Only |  | 0
Progress % |  | 94%
# | Module | Feature | Description | Backend Status | Frontend Status | Overall Status | Client Approval | Priority | Notes
1 | Employee Portal | Employee Dashboard | Summary: payslip, leave balance, attendance | Complete | Complete | Complete | Approved | High
2 | Employee Portal | View Profile | Personal, employment details read-only view | Complete | Complete | Complete | Approved | High
3 | Employee Portal | Update Profile | Self-edit personal details | Complete | Complete | Complete | Approved | High
4 | Employee Portal | View & Update Bank Details | Self-service bank account management | Complete | Complete | Complete | Approved | High
5 | Payslips | View Payslip History | List payslips by year with detail modal | Complete | Complete | Complete | Approved | High | Enhanced with bank, UAN, ESI, leave data
6 | Payslips | Download Payslip PDF | Download individual payslip as PDF | Complete | Complete | Complete | Approved | High
7 | Leave | Apply for Leave | Submit leave request with type and dates | Complete | Complete | Complete | Approved | High
8 | Leave | View Leave Balance | Remaining leave days by type | Complete | Complete | Complete | Approved | High
9 | Leave | Leave History & Cancel | View past requests, cancel pending ones | Complete | In Progress | In Progress | Approved | Medium | Cancel modal exists; confirmation flow partial

## 🔍 Auditor
AUDITOR — FEATURE TRACKING
HR Payroll System ¦ 08 Mar 2026
Total |  | 5
Complete |  | 0
In Progress |  | 0
Partial |  | 0
Not Started |  | 4
API Only |  | 1
Progress % |  | 10%
# | Module | Feature | Description | Backend Status | Frontend Status | Overall Status | Client Approval | Priority | Notes
1 | Auditor | Auditor Dashboard | Summary view for audit access | Complete | Not Started | API Ready / UI Pending | Pending | Medium | API endpoint exists; no frontend page yet
2 | Auditor | Wage Statement Audit View | Read-only payroll data for auditor | In Progress | Not Started | Not Started | Pending | Medium | auditor.py endpoint stub
3 | Auditor | Audit Trail / Logs | Track all data changes with timestamp | Not Started | Not Started | Not Started | Pending | High | audit_service.py exists but not wired to endpoints
4 | Auditor | Statutory Compliance Report | Compliance summary for auditor review | Not Started | Not Started | Not Started | Pending | Medium | Planned; not started
5 | Auditor | Export Audit Data | Export audit logs to Excel/PDF | Not Started | Not Started | Not Started | Pending | Low | Planned; not started

## ⚙️ System-Platform
SYSTEM/PLATFORM — FEATURE TRACKING
HR Payroll System ¦ 08 Mar 2026
Total |  | 16
Complete |  | 9
In Progress |  | 1
Partial |  | 0
Not Started |  | 6
API Only |  | 0
Progress % |  | 59%
# | Module | Feature | Description | Backend Status | Frontend Status | Overall Status | Client Approval | Priority | Notes
1 | Auth & Security | JWT Login / Logout | OAuth2 password bearer, token refresh | Complete | Complete | Complete | Approved | High
2 | Auth & Security | Role-Based Access Control | Admin, employer, HR manager, employee, auditor roles | Complete | Complete | Complete | Approved | High | Protected routes + API dependency guards
3 | Auth & Security | Password Change | User self-service password reset | Not Started | Not Started | Not Started | Pending | Medium | No endpoint implemented yet
4 | Multi-Tenancy | Tenant Isolation | Schema/row-level data isolation per org | Complete | Not Started | In Progress | In Review | High | Middleware exists; full isolation testing pending
5 | Database | PostgreSQL Migration (Alembic) | DB schema versioning via Alembic | Complete | Not Applicable | Complete | Approved | High | 7 migration versions applied
6 | API | REST API (FastAPI) | Full OpenAPI spec, Swagger UI at /docs | Complete | Not Applicable | Complete | Approved | High
7 | API | Health Check Endpoint | GET /api/v1/health | Complete | Not Applicable | Complete | Approved | Low
8 | File Processing | Excel Upload Processing | Employee, attendance, wage Excel parsing | Complete | Complete | Complete | Approved | High | pandas + openpyxl pipeline
9 | PDF Generation | Payslip PDF Engine | ReportLab-based professional payslip PDF | Complete | Not Applicable | Complete | In Review | High | Indian currency words, two-color scheme
10 | Notifications | Email Notifications (SMTP) | Payslip email delivery via SMTP | Complete | Not Applicable | Complete | Pending | Medium | SMTP config required; email_service.py done
11 | Notifications | WebSocket Notifications | Real-time in-app notifications | Not Started | Not Started | Not Started | Pending | Low | notifications.py stub exists; not wired
12 | Notifications | Attendance Upload WS | WebSocket progress for bulk upload | Not Started | Not Started | Not Started | Pending | Low | attendance_upload.py stub exists
13 | Background Tasks | Payroll Batch Processing | Async batch payroll calculation | Not Started | Not Applicable | Not Started | Pending | Medium | payroll_batch.py stub; not wired to scheduler
14 | Background Tasks | Data Cleanup Tasks | Periodic data archival and cleanup | Not Started | Not Applicable | Not Started | Pending | Low | data_cleanup.py stub exists
15 | Docker | Docker / docker-compose | Containerised deployment setup | Complete | Not Applicable | Complete | Not Required | Medium | Dockerfile + docker-compose.yml ready
16 | Testing | Automated Test Suite | pytest unit + integration tests | Not Started | Not Applicable | Not Started | Not Required | Medium | pytest.ini configured; test files mostly stubs

## 📝 Change Log
CHANGE LOG
Date | Version | Stakeholder | Feature / Change | Status | Updated By | Notes
| 2026-03-08 | v1.5 | Employer/HR | Payslip PDF redesign — Indian currency words, bank/UAN/ESI data | Complete | Claude AI | Matches reference payslip format
| 2026-03-08 | v1.5 | Employee | EmployeePayslips.jsx — enhanced data display with new API fields | Complete | Claude AI
| 2026-03-08 | v1.5 | System/Platform | CORS fix: 127.0.0.1 → localhost, axios fallback port 8001→8000 | Complete | Claude AI
| 2026-03-08 | v1.5 | All | Project cleanup: removed 24 stale files, credential docs unified | Complete | Claude AI | CREDENTIALS_AND_CONFIG.md created
| 2026-01-18 | v1.4 | Employer/HR | Holiday Calendar + Working Calendar UI | Complete | Dev Team
| 2026-01-18 | v1.4 | Employer/HR | PayrollDashboard with bulk operations | Complete | Dev Team
| 2026-01-18 | v1.4 | System/Platform | Wage template service + Excel parser enhancements | Complete | Dev Team
| 2025-xx-xx | v1.3 | Employee | All employee features fixed (leave, profile, payslips) | Complete | Dev Team
| 2025-xx-xx | v1.2 | System/Platform | PostgreSQL migration + leave types + salary structure | Complete | Dev Team | 10 employees seeded
| 2025-xx-xx | v1.1 | Employee | Leave management fixed | Complete | Dev Team
| 2025-xx-xx | v1.0 | All | Initial commit — base HR Payroll scaffold | Complete | Dev Team